## Add to Cart functionality
PROJECT NAME |  | Benefit Store
PREPARED BY |  | Surya Joshi
DESIGNATION |  | QA Intern
DATE |  | 2025-02-27
SCENARIO ID | TS_004 | SCENARIO DESCRIPTION |  |  | Validate the workig of Add to Cart functionality
S.NO | TEST CASE ID | TEST CASE DESCRIPTION | PRECONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS | DEFECT ID | COMMENTS
1 | TC-CF_001 | Validate display of selected plan in cart. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. | N/A (Verify existing data) | Selected plan should be displayed with the correct total price. | Selected plan is displayed with the correct total price. | Passed
2 | TC-CF_002 | Validate the breadcrumb nagivation. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Check theBreadcrumb. | N/A (Verify existing data) | 1.Home must navigate to the homepage. 2. cart leads to the Mycart 3. Clicking plans navigates to Plans Page with all list and component with UI | Breadcrumb navigation is correctly working nad redirecting to the associated pages. | Passed
3 | TC-CF_003 | Validate display of "Order Info" section. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Check the details. | N/A (Verify existing data) | The "Order Info" section is displayed, showing "Effective Date," "One Time Processing Fee," "First Month Cost," "Recurring Cost," and "Total Cost." | The "Order Info" section is displayed and showing "Effective Date," "One Time Processing Fee," "First Month Cost," "Recurring Cost," and "Total Cost." | Passed
4 | TC-CF_004 | Validate effective date dropdown values and selection. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click on "Effective Date" dropdown. 6. Select the Valid Date. | Valid Dates (e.g., 05/01/2025, 06/01/2025, 07/01/2025). | The "Effective Date" dropdown contains valid dates; | The "Effective Date" dropdown contains valid dates; | Passed
5 | TC-CF_005 | Validate display and calculation of costs. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Verify the displayed costs for "One Time Processing Fee," "First Month Cost," "Recurring Cost," and "Total Cost." | N/A (Verify existing data) | "One Time Processing Costs", "First Month Cost", "Recurring Cost" and "Total Costs" should be valid. | "One Time Processing Costs", "First Month Cost", "Recurring Cost" and "Total Costs" are valid and accurate. | Passed
6 | TC-CF_006 | Validate "Proceed to Checkout" button. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "Proceed to Checkout" button. | N/A | The popup should be displayed to proceed to enrollemnt or back to cart button and displaying the effective date. | The popup is dsplayed to proceed to enrollemnt or back to cart button and displaying the effective date. | Passed
7 | TC-CF_007 | Validate the text "Cart page confirmation to proceed further" | User has successfully navigated to the "Cart" page and cllicked " Proceed to Checkout" button. | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "Proceed to Checkout" button. | N/A | The text should be displayed at the top of the popup window | The text is displayed at the top of the popup window. | Passed
8 | TC-CF_008 | Validate the image and the text below the image "Your plans will be effective as of {Effective Date}" is displayed correctly. | User has successfully navigated to the "Cart" page and cllicked " Proceed to Checkout" button. | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "Proceed to Checkout" button. | N/A | The image and the text having the image should be available and valid . | The image and the text having the image are present and valid . | Passed
9 | TC-CF_009 | Validate "Proceed to Enrollment " button in the popup. | User has successfully navigated to the "Cart" page and cllicked " Proceed to Checkout" button. | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "Proceed to Checkout" button. | N/A | The user should be redirected to the "enrollment/ personal-info" page | The user is redirected to "enrollment/ personal-info" page | Passed
10 | TC-CF_010 | Validate Back to Cart " button in the popup. | User has successfully navigated to the "Cart" page and cllicked " Proceed to Checkout" button. | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "Proceed to Checkout" button. | N/A | The user should be redirected back to he cart page | The user is redirected back to he cart page | Passed
11 | TC-CF_011 | Validate "Continue Shopping" button. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "Continue Shopping" button. | N/A | The application should be redirected to the plans page. | The user is redirected to the plans page. | Passed
12 | TC-CF_012 | Validate the delete plan icon. | User has successfully navigated to the "Cart" page | 1. Navigate to the website. 2. fill out the form. 3. select the desired plan. 4. Add plan to cart. 5. Click the "delete" icon. | N/A | Clicking the delete icon should delte the plan and update the costs. | Plan got deleted from the cart. | Passed
13 | TC-CF_013 | Validate all buttons, texts as per the requirements. | User has successfully navigated to the "Cart" page | 1. Fonts must be consistence with all other pages 2. Must be clickable | N/A | UI should be according to the requirement documentation. | UI is set according to the requirement documentation. | Passed
14 | TC-CF_014
15 | TC-CF_015
16 | TC-CF_016
17 | TC-CF_017
18 | TC-CF_018
19 | TC-CF_019